PROJECT BRIEF

AI-Assisted Research Framework

Claude Code MVP  ·  Capital One UX Research

| Delivery Date | May 12, 2026 |
| --- | --- |
| Project Lead | Shoshana, Director of UX Research |
| Build Method | Claude Code · Team-led development |
| Requested By | Research MVP (Managing VP) |
| Status | In Planning — Kickoff Week of Apr 28 |

# 1  Background & Strategic Context

Capital One's UX Research team operates a 10-question research framework that spans the full product lifecycle — from discovery through in-market assessment. Today, that framework is executed manually: researchers decide which questions apply, select methods, design instruments, and structure deliverables largely from scratch each time.

The Research MVP has sponsored a two-week sprint to build an AI-assisted version of this framework in Claude Code. The goal is to create a system where researchers can enter a project brief and receive structured, ODI-grounded deliverable scaffolds for each applicable question — reducing ramp time, increasing consistency, and enabling the team to take on more research with the same capacity.

This project sits at the intersection of two parallel workstreams:

- A JTBD data product being built by a separate team that will eventually house the full ODI taxonomy and allow direct API access to validated job and outcome statement data.

- A library of foundational research containing existing user needs context across Capital One's core product areas.

The MVP bridges these two workstreams with a Knowledge Mapper component — a skill that extracts and translates existing research context into ODI-compatible inputs, so the downstream modules can function before the JTBD data product is available.

# 2  Problem Statement

Researchers spend significant time on framework setup work — deciding which methods apply, structuring study plans, designing evaluation criteria, and formatting deliverables — before any primary research begins. This setup work is largely repeatable but currently done from scratch, creating inconsistency in output quality and slowing time-to-insight.

Simultaneously, the team has accumulated substantial foundational research that is difficult to access and apply systematically. Insights from prior studies are not in a structured format that can inform new research planning without significant manual effort.

The result: researchers operate below their potential contribution because too much time is spent on scaffolding rather than sense-making.

# 3  Goals & Success Criteria

## Primary Goals

- Deliver a working Claude Code system that covers all 10 research framework questions by May 12.

- Enable a researcher to enter a project brief and receive structured deliverable scaffolds for each applicable question without manual setup.

- Ground all module outputs in ODI/JTBD logic — using existing foundational research as the context source for MVP.

## Success Criteria (Gate 4 — May 12)

- All 10 modules produce structured, phase-appropriate deliverable drafts.

- Orchestrator correctly routes based on project phase and selected question(s).

- A researcher can enter a real project brief and receive actionable output with no manual pre-configuration.

- Outputs have been reviewed against at least one real Capital One project context.

- Handoff documentation exists so a team member not involved in the build can extend the system.

## Out of Scope for MVP

- Integration with the JTBD data product API (targeted for post-MVP).

- UI layer — system runs in Claude Code terminal for MVP.

- Quantitative opportunity scoring — Ulwick scoring requires data not available at runtime.

- Post-research synthesis modes for Q2, Q9, Q10 — planning modes only for MVP.

# 4  System Architecture

The system is organized into three layers: a routing orchestrator, 10 research modules, and a set of shared foundation components that all modules depend on.

## Component Overview

| Q# | Module | Deliverable | Type | MVP Priority |
| --- | --- | --- | --- | --- |
| — | Knowledge Mapper | ODI-ready context from existing research | Skill | Required |
| — | Orchestrator | Routing + context enrichment | Agent | Required |
| Q1 | Needs Requirements | Needs Requirements doc | Skill | Simplified |
| Q2 | Experience Gap Analysis | Experience Gap Analysis | Skill/Agent | Simplified |
| Q3 | Feature Prioritization | Feature Prioritization | Skill | Required |
| Q4 | Beacon Report | Beacon Report | Agent | Simplified |
| Q5 | Metrics Map | Metrics Map | Skill | Required |
| Q6 | Concept Comparison | Concept Comparison guide | Skill | Required |
| Q7 | Testing Results | Testing plan + findings template | Skill | Required |
| Q8 | Pilot Results | GA Readiness checklist | Skill | Deferrable |
| Q9 | Experience Assessment: Usefulness | Usefulness diagnostic | Skill | Simplified |
| Q10 | Experience Assessment: Usability | Usability diagnostic | Skill | Simplified |

Type indicates whether the component requires tool use and mid-run decision making (Agent) or is a pure reasoning-to-output transformation (Skill). MVP Priority indicates build investment level: Required = full build; Simplified = scoped-down version; Deferrable = checklist/template only if time is short.

## Knowledge Mapper — Key Design Note

Rather than building Q1 as a generative module for MVP, the team will build a Knowledge Mapper skill that extracts existing research context and translates it into ODI-compatible inputs (job statements, outcome statement drafts) that feed all downstream modules.

This approach is grounded in the team's existing foundational research and avoids building a generative module with a short shelf life — once the JTBD data product is available, the Knowledge Mapper will be updated to call that API instead of processing research documents.

Critical requirement: the Knowledge Mapper must perform ODI translation, not just extraction. Research findings expressed as pain points, themes, or HMW statements must be converted to outcome statement format before being passed downstream. This is where the most prompt engineering investment should be concentrated.

# 5  Schedule & Gates

The project runs two weeks from Apr 28 to May 12. Four quality gates define the checkpoints at which work is reviewed before the next phase begins.

| Gate | Pass Criteria |
| --- | --- |
| Gate 1 Architecture Locked Apr 29 | - Architecture decision doc complete — component types and responsibilities resolved - Context schema defined and stress-tested against 3 real project types - Base module template and output formatter scaffolded - Knowledge Mapper approach agreed — extraction + translation design confirmed |
| Gate 2 Discovery Complete May 2 | - Knowledge Mapper producing ODI-compatible context from at least one real research corpus - All 5 Discovery modules producing usable deliverable drafts - Outputs reviewed against a real Capital One project context - Orchestrator routing correctly to all Discovery modules |
| Gate 3 All 10 Modules Complete May 8 | - All 10 modules producing structured deliverable drafts - Each output reviewed by at least one team member for quality - No module producing blank or malformed output on valid input - Orchestrator routing correctly across all three phases |
| Gate 4 Ready to Ship May 12 | - Full end-to-end test passed: real project brief through all 10 modules - Edge cases documented - Demo script prepared and rehearsed - Handoff doc written |

# 6  Scope Management

## If the Timeline is at Risk

Cut in this order. These reductions preserve core system function while reducing build complexity:

- Cut 1: Q8 Pilot Results

- Reduce to a fixed GA readiness checklist. No contextual generation needed.

- Cut 2: Q4 Beacon Report

- Reduce to a structured search-prompt scaffold the researcher executes manually.

- Cut 3: Phase integration tests

- Collapse D6, P4, I3 into the single end-to-end test (DEL1). Saves ~1.5 days.

- Cut 4: Output formatter

- Bake formatting into each module prompt rather than building a separate component.

- Cut 5: Handoff doc

- Reduce to a README — three sections: decisions, extension guide, known gaps.

## Do Not Cut

The following are non-negotiable for MVP to be useful:

- Knowledge Mapper — ODI translation layer specifically

- Orchestrator — routing + context enrichment

- Context schema — full definition on Day 1

- Q3 Feature Prioritization

- Q5 Metrics Map

- Q7 Testing Results (planning mode)

- End-to-end integration test and demo script

# 7  Risks & Mitigations

| Risk | Likelihood | Mitigation |
| --- | --- | --- |
| Knowledge Mapper produces surface-level extraction without true ODI translation | High | Invest most prompt engineering effort here. Validate output against ODI compliance criteria before using in any downstream module. |
| Context schema too thin to support all 10 modules | Medium | Stress-test schema against 3 diverse project types on Day 1 before any module is built. |
| Q2/Q9/Q10 mode ambiguity (planning vs. synthesis) creates confusing outputs | Medium | Scope all three to planning mode only for MVP. Document synthesis mode as post-MVP. |
| Q4 Beacon Report requires live search that isn't available | Medium | Reduce to search-prompt scaffold for MVP. Flag as post-MVP enhancement when agent capability is confirmed. |
| Team builds modules inconsistently without shared template | Low | Enforce base module template at Gate 1. Review first two modules built before others proceed. |
| JTBD data product timeline creates integration rework | Low | Knowledge Mapper is designed as a replaceable integration layer. Architecture decision doc should document this explicitly so the swap is clean. |

# 8  Post-MVP Roadmap

The following are explicitly deferred from this sprint and represent the natural next phase of investment:

- JTBD data product integration — replace Knowledge Mapper document processing with direct API calls to the validated taxonomy.

- Q1 generative module — once the data product is live, build Q1 as a full generative skill that produces ODI-compliant needs requirements from the taxonomy.

- Synthesis modes for Q2, Q9, Q10 — extend these modules to process post-research outputs in addition to generating planning scaffolds.

- Q4 Beacon Report as a full agent — implement with live web search for real-time competitive pattern synthesis.

- UI layer — move from Claude Code terminal to a researcher-facing interface, likely integrated with existing team tooling.

- Quantitative opportunity scoring — integrate with A/B test and analytics data to enable Ulwick-style importance × satisfaction scoring in Q3.

# 9  Approvals & Sign-off

This brief is submitted for review and approval prior to kickoff on April 28, 2026.

| Project Lead | Research MVP | Reviewing Manager |
| --- | --- | --- |
| Signature / Date | Signature / Date | Signature / Date |